## GY-25-26 PBC HIV P&A Workplan
GY-25-26 Priorities & Allocations Committee Work Plan
The work plan is intended to help guide the work of the committee and to assist the Priorities & Allocations Committee in achieving its objectives in the coming year.
For each activity, the time period of activity is highlighted in blue and the completion date is noted with an “X”.
GOAL: Develop integrated P&A process using data with input from stakeholders and consumer forums
Objective 1: Plan, prioritize, allocate and monitor available resources and expenditures
Activities | Frequency | Responsible Party | Outcomes | Action Items/Data Prep | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb
1.1 Review data relevant to the Priorities & Allocation process (including recommendations from QMEC, Planning and Community Awareness) | Ongoing | Receipient Staff/ P&A | Data driven P&A process | a. P&A Service Category Scorecards (utilization, expenditures, etc.) b. Community input (through focus groups and P&A Members training to view data, Planning Committee forums, etc.) c. Epidemiology (including incidence, prevalence, co-morbidities, etc.) d. Unmet Need e. Implementation Plan f. Cost data (other funders) g. QM Care Continuum measures | bar: May to Aug
1.2 Review How Best to Meet the Need language recommendations from Planning committee. | Annually |  | Data driven P&A process | Review and update How Best to Meet the Need language recommendations from Planning committee. | bar: June to Aug
1.3 Priority rank Part A and MAI service categories | Annually |  | Complete P&A process | Use data elements to inform priority ranking process. (PSRA) | bar: June to Aug
1.4 Allocate Part A and MAI funds by service category | Annually | P&A | Complete P&A process | Allocate Part A and MAI funds based on priority ranking process. | bar: June to Aug
1.5 Priority setting & ResourceAllocation PROCESS PRESENTATION | Annually | P&A | Training Member | Taining to members to learn about the process of deciding which HIV/AIDS services are the most important according to the criteria your EMA/TGA has established | bar: May to June; Nov
1.6 Monitor expenditures and allocations | Bi-Annually | P&A/ Recipient | Appropriate funding | Recommend reallocations (“Sweeps”) to ensure sufficient core funding and the distribution of additional funds. | bar: Mar to Feb
1.7 Review and approve GY-25-26 P&A Work Plan | Annually | P&A | Process Planning | bar: Mar to Feb
Objective 2: Establish a seamless system between care and treatment to facilitate access and ensure linkage and retention
(Integrated Plan Strategy 2.1.a)
Activities |  | Responsible Party | Outcomes | Action Items/Data Prep | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb
2.1 Develop targeted strategies and interventions for vulnerable populations who may not seek care or who may have fallen out of care (YEAR 1-2) | As Needed/ Recommended | P&A | Increase access to care and improve health outcomes | Review recommendations from QMEC, Integrated Work Group, Planning Committee and other relevant data sources to identify and develop strategies to address the needs of clients who may not seek care or who have fallen out of care. Implement identified strategies for MAI funded services in the EMA through Service Delivery Models, programs, interventions, enhanced service categories. | bar: June to Aug
Objective 3: Assess the Administrative Mechanism
Activities |  | Responsible Party | Outcomes | Action Items/Data Prep | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb
3.2 Assessment of the Administrative Mechanism recommendations | Annually | P&A | Ensure compliance | Make recommendations for activities to include in the assessment of the Administrative Mechanism. | bar: Mar to May